## GANTT TIMELINE
ALCHE — 24-Month Operational Roadmap
TASK | OWNER | Q1 (M1-M3) |  |  | Q2 (M4-M6) |  |  | Q3 (M7-M9) |  |  | Q4 (M10-M12) |  |  | Q5 (M13-M15) |  |  | Q6 (M16-M18) |  |  | Q7 (M19-M21) |  |  | Q8 (M22-M24)
TASK | OWNER | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
FUNDRAISE
Close pre-seed (EUR 500K) | Timu | ●
Monthly investor updates | Timu
Seed round prep (data room, deck) | Timu | [11 empty] | ●
Seed active outreach | Timu
Seed round close | Timu | [22 empty] | ●
PRODUCT
App wireframes & MVP spec | Timu |  |  | ●
MVP development (EUR 20K) | Contractor |  |  |  | ●
App public launch | Timu |  |  |  | ●
Contractor ongoing (EUR 12K/mo) | Contractor
HealthKit / Health Connect integration | Contractor | [5 empty] | ●
Retention features (streaks, notifications) | Contractor | [7 empty] | ●
AI personalization v1 | Contractor | [8 empty] | ●
Blood panel integration | Contractor | [9 empty] | ●
Technical debt audit & DPIA | Timu | [11 empty] | ●
Product v2 planning | Timu | [14 empty] | ●
CTO takes over product | CTO | [17 empty] | ●
Product v2 development | CTO + Eng | [22 empty] | ●
App v2 public release | CTO | [23 empty] | ●
BRAND & CONTENT
Brand identity finalization | Timu | ●
Website + waitlist launch | Timu |  | ●
Content engine (social, newsletter) | Timu
PR push (press kit, media outreach) | Timu | [6 empty] | ●
Podcast guesting strategy | Timu + Daria
SEO strategy implementation | Timu
Case studies published | Comm Mgr | [11 empty] | ●
Daria thought leadership | Daria
OPERATIONS
GmbH incorporation | Timu | ●
Space search & lease signing | Daria |  | ●
Ablöse + Kaution paid (EUR 57.5K) | Daria |  | ●
Space buildout | Daria |  |  | ●
Compliance (HACCP, DSB, insurance, GEMA) | Daria |  |  |  | ●
Space grand opening | Daria |  |  |  | ●
Space staff hired (Midijob) | Daria |  |  |  | ●
Partner / Community Manager hired | Daria | [5 empty] | ●
Supply chain maturation | Daria
CTO search initiated | Timu
CTO interviews & selection | Timu | [16 empty] | ●
CTO hired & onboarded | Timu | [17 empty] | ●
First engineer hired | CTO | [19 empty] | ●
Second engineer hired | CTO | [22 empty] | ●
Second location prep | Daria
Tax & corporate structure review | Daria
COMMUNITY
Waitlist building (target: 500) | Timu |  |  | ●
Beta tester cohort (20-30 people) | Timu |  |  |  | ●
Founding member onboarding | Timu |  |  |  | ●
Product-market fit assessment | Timu | [5 empty] | ●
Referral program launch | Comm Mgr | [8 empty] | ●
Ambassador program (10 users) | Comm Mgr
Community platform (Slack/WhatsApp) | Comm Mgr
COMMERCIAL
Retail supplier agreements | Daria |  |  | ●
Payment infra (Stripe + SumUp POS) | Timu |  |  |  | ●
First smoothie + retail sales | Daria |  |  |  | ●
App subscriptions live (EUR 19/49/99) | Timu |  |  |  | ●
Gift cards launched | Timu |  |  |  | ●
Events launch (EUR 35/ticket) | Comm Mgr | [5 empty] | ●
CGM affiliate launch (EUR 15/user/mo) | Daria | [6 empty] | ●
B2B corporate pilot (EUR 39 PEPM) | Daria | [8 empty] | ●
Annual subs launched (EUR 190/490/990) | Timu | [8 empty] | ●
Doctor SaaS (EUR 99/mo per clinic) | Daria | [10 empty] | ●
Retail e-commerce launch | Timu | [12 empty] | ●
Break-even validated | Both | [14 empty] | ●
Retail scaling to 4,600 units/mo | Daria | [23 empty] | ●
B2B: 3 active clients | Daria | [23 empty] | ●

## MONTHLY DETAIL
Month | Quarter | Strategic Theme | Subscribers | Monthly Revenue | Monthly Burn | Cash Position | Team Size | Key Milestones | Critical Decisions | Risks to Watch
M1 | Q1 | Close & Incorporate | 0 | 0 | 12000 | 488000 | 2 | Pre-seed closed, GmbH filed, Brand identity done | GmbH vs UG; SAFE vs Note; Vesting | Round delay
M2 | Q1 | Lease & Wireframe | 0 | 0 | 72000 | 416000 | 2 | Lease signed (€57.5K out), App wireframes, Compliance started | Space location; App architecture | Lease negotiation; Ablöse
M3 | Q1 | Build & Prepare | 0 | 0 | 30000 | 386000 | 2 | Space buildout, MVP dev starts, Suppliers signed, 500 waitlist | Contractor selection; Retail range | Buildout overruns
M4 | Q2 | Doors Open | 15 | 5000 | 22000 | 369000 | 3 | SPACE OPENS, App launch, First sales, Staff hired | Public vs beta launch; Hours | Low foot traffic
M5 | Q2 | Iterate & Optimize | 29 | 8000 | 30000 | 347000 | 3 | Contractor starts (€12K/mo), Retail optimization | Sprint priorities | Contractor quality
M6 | Q2 | Expand Offering | 42 | 15000 | 32000 | 330000 | 4 | Community Mgr hired, First event, PMF assessment | Event format; Pricing validation | PMF signals weak
M7 | Q3 | Second Wave | 61 | 22000 | 32000 | 320000 | 4 | CGM affiliate launch, PR push, Retention features | CGM partner; PR approach | Low CGM adoption
M8 | Q3 | Operational Cadence | 78 | 30000 | 32000 | 318000 | 4 | B2B prep, Supply chain matured, Analytics deployed | B2B pricing; Supplier terms | B2B sales cycle
M9 | Q3 | B2B Activation | 94 | 40000 | 33000 | 325000 | 4 | First B2B client, Annual subs, Community flywheel | Annual pricing; B2B pilot scope | Client delays
M10 | Q4 | Scale Signals | 114 | 55000 | 33000 | 347000 | 4 | Retail scaling, Seed prep begins, CTO search starts | E-commerce; CTO comp level | Retail volume
M11 | Q4 | Approaching Breakeven | 133 | 70000 | 34000 | 383000 | 4 | Revenue optimization, DPIA done, Doctor SaaS starts | Pricing adjustments | Churn > 8%
M12 | Q4 | Breakeven Milestone | 150 | 80000 | 34000 | 429000 | 4 | BREAKEVEN, Seed narrative ready, Year 1 review | Seed timing; 2nd location feasibility | Break-even delayed
M13 | Q5 | Year 2 Begins | 170 | 95000 | 34000 | 490000 | 4 | E-commerce launch, 2nd B2B client, Tax planning | E-commerce platform | Tax liability
M14 | Q5 | CTO Pipeline | 188 | 105000 | 35000 | 560000 | 4 | CTO interviews, Product v2 planning | CTO candidate profile | Budget too low
M15 | Q5 | EBITDA Positive | 205 | 115000 | 35000 | 640000 | 4 | EBITDA POSITIVE, Seed outreach active | Reinvest vs preserve cash | Profitability fragile
M16 | Q6 | Scale Prep | 221 | 130000 | 35000 | 735000 | 4 | CTO offer extended, Seed meetings active | Seed round size | CTO drops out
M17 | Q6 | CTO Notice Period | 235 | 140000 | 35000 | 840000 | 4 | CTO accepted, serving notice | CTO equity package | Notice period
M18 | Q6 | Technical Maturity | 248 | 155000 | 45000 | 950000 | 5 | CTO DAY 1, Engineering roadmap, Data room complete | Seed valuation; 2nd location commit | CTO ramp-up
M19 | Q7 | Growth Engine | 266 | 180000 | 50000 | 1080000 | 5 | First engineer hired, v2 Sprint 1 | Engineer profile | Hiring competition
M20 | Q7 | Momentum | 283 | 195000 | 55000 | 1220000 | 6 | Retail 1,500+ units, Seed term sheets | Seed investor selection | Retail gap
M21 | Q7 | Seed Negotiation | 298 | 210000 | 55000 | 1380000 | 6 | App v2 beta, International markets evaluated | Expansion markets | Seed negotiation
M22 | Q8 | Close & Scale | 312 | 230000 | 60000 | 1550000 | 6 | Seed legal docs, 2nd location LOI | Seed final terms | Round delay
M23 | Q8 | Final Push | 325 | 250000 | 60000 | 1740000 | 7 | SEED CLOSED, App v2 release, 2nd engineer | Board composition | Post-seed execution
M24 | Q8 | Milestone | 337 | 264000 | 65000 | 1940000 | 7 | M24 TARGETS, 4,600 units, 337 subs, Year 3 plan | Year 3 strategy | Retail target miss

## DECISIONS
ID | Decision | Deadline (Week) | Owner | Blocks | Options / Notes | Status
D1 | GmbH vs UG incorporation | W1 | Timu + Legal | All contracts | GmbH preferred (investor optics) | OPEN
D2 | Vesting schedule & ESOP pool | W2 | Timu + Daria | Cap table | 4yr/1yr cliff; 10-15% pool | OPEN
D3 | SAFE vs Convertible Note | W1 | Timu + Legal | Round close | SAFE simpler; DE investors may prefer note | OPEN
D4 | Space location (neighborhood) | W6 | Daria | Lease, buildout | Mitte / P-Berg / Kreuzberg / F-hain | OPEN
D5 | App tech architecture | W6 | Timu | MVP spec | React Native vs Flutter; backend stack | OPEN
D6 | Fractional CTO vs tech advisor | W8 | Timu + Daria | Technical quality | Fractional (€3-5K/mo) vs equity advisor | OPEN
D7 | Retail supplier selection | W14 | Daria | Inventory | 3-5 brands, EU compliant, NO NMN | OPEN
D8 | App contractor selection | W12 | Timu | M5 dev start | Agency vs freelancer | OPEN
D9 | Event format & pricing | W20 | Daria | M6 event | Workshop €35 / Talk €20 / Social free | OPEN
D10 | Gift card platform | W14 | Timu | M4 launch | Square / Shopify / custom | OPEN
D11 | Payment infrastructure | W13 | Timu | Space opening | Stripe (app) + SumUp (POS) | OPEN
D12 | B2B pricing validation | W28 | Daria | M9 pilot | €39 PEPM competitive? | OPEN
D13 | CGM affiliate partner | W26 | Daria + Doctor | M7 launch | Abbott / Dexcom / other | OPEN
D14 | Retail e-commerce platform | W37 | Timu | Online retail | Shopify / WooCommerce / custom | OPEN
D15 | Annual subscription launch timing | W32 | Timu | Deferred revenue | €190/490/990 (~17% discount) | OPEN
D16 | CTO compensation level | W40 | Timu + Daria | CTO search | €78K budgeted < market (€80K+). Increase? | OPEN
D17 | Seed round timing | W44 | Timu | Fundraise prep | M18 / M20 / M22 | OPEN
D18 | Second location feasibility | W48 | Daria | Expansion | Go/no-go for seed narrative | OPEN
D19 | E-commerce investment level | W42 | Timu | Marketing spend | Low / Medium / High | OPEN
D20 | CTO final candidate | W58-62 | Timu + Daria | M18 hire | Technical + culture + leadership | OPEN
D21 | Reinvest vs preserve cash | W56 | Timu | Growth spend | More growth vs stronger cash position | OPEN
D22 | Product v2 scope | W60 | Timu | CTO brief | AI depth, social, B2B tools | OPEN
D23 | Seed round size | W68 | Timu + Daria | Investor talks | €2M / €3M / €5M | OPEN
D24 | Seed valuation expectations | W70 | Timu | Term sheets | Revenue-based (2-4x) vs ARR (8-15x) | OPEN
D25 | Second location: commit or defer | W72 | Daria | CapEx | Commit (€75-120K) vs deepen L1 | OPEN
D26 | CTO equity package | W66 | Timu + Legal | Offer letter | 1-3% typical post-seed CTO | OPEN
D27 | Seed investor selection | W84 | Timu + Daria | Round close | Strategic vs financial VC | OPEN
D28 | Engineering team size Y3 | W80 | CTO | Hiring plan | CTO+2 (lean) vs CTO+4 (aggressive) | OPEN
D29 | International expansion markets | W82 | Daria | Seed narrative | DACH / UK / other | OPEN
D30 | Seed final terms & close | W92-96 | Timu | Capital deploy | Final negotiation | OPEN
D31 | Year 3 strategic plan | W100 | All | Resource allocation | Multi-location vs depth vs geo | OPEN
D32 | Board composition | W96 | Timu + Lead investor | Governance | 3 vs 5 seats; observers | OPEN

## RISKS
ID | Risk | Likelihood | Impact | Owner | Mitigation | Early Warning | Status
R1 | Pre-seed takes longer than M1 | H | H | Timu | Bridge savings; parallel-track GmbH | W3 no term sheet | OPEN
R2 | Space lease delays (M4→M5-6) | M | H | Daria | Start search W3; backup properties | W8 no lease | OPEN
R3 | Retail volume M24 unrealistic (4,600 units, 92% non-sub) | H | H | Daria | E-commerce M13; wholesale M20; adjust model | M6 retail <80 units | OPEN
R4 | App contractor late/poor quality | M | H | Timu | Milestone payments; backup contractor | Sprint 1 >50% late | OPEN
R5 | CTO salary below market (€78K < €80K 25th pct) | H | M | Timu | Increase to €90-110K; offset with equity | W43 <3 candidates | OPEN
R6 | NMN not EU Novel Food approved | L | M | Daria | Exclude from Day 1; monitor regulation | Supplier offers NMN | OPEN
R7 | Monthly churn exceeds 8% | M | H | Timu | Onboarding investment; retention features | M5 churn >12% | OPEN
R8 | Smoothie bar HACCP/permit delays | L | M | Daria | Start HACCP W7; book Gesundheitsamt early | W11 no HACCP | OPEN
R9 | Cash trough M3-4 tighter than modeled | M | H | Timu + Daria | Keep €50K buffer; phase CapEx | Cash <€300K at M3 | OPEN
R10 | B2B sales cycle >3 months | M | M | Daria | Start pipeline M7; offer free pilot | M8 zero leads | OPEN
R11 | Founder burnout (2-person, 6+ months) | H | H | Both | Hire M4+M6; protect weekends | Exhaustion at W8+ | OPEN
R12 | Seed round doesn't close | M | H | Timu | Stay profitable; alternative funding | M20 zero term sheets | OPEN
R13 | Competitor enters Berlin longevity | M | M | Daria | Move fast; community moat; exclusives | Competitor launch | OPEN
R14 | Data breach / GDPR violation | L | H | Timu + DSB | DPIA; encryption; cyber insurance | Any complaint | OPEN
R15 | Key supplier failure | M | M | Daria | Multi-source top SKUs; 30-day safety stock | Missed delivery | OPEN
R16 | Sub revenue too low for SaaS valuation (5% of M24) | H | M | Timu | Reframe: hybrid commerce+tech (2-4x rev) | Investor pushback | OPEN

## TEAM & COST
ALCHE — Team Ramp & Cost Overview
Role | Start Month | Gross/Month (€) | Employer Cost (€) | Equity | Notes
Timu (CEO) | M1 | 4166 | 5208 | Co-founder | Brand, product, fundraise
Daria (COO) | M1 | 4166 | 5208 | Co-founder | Ops, retail, partnerships
Space Staff (Midijob) | M4 | 1230 | 1538 | — | 25 hrs/week
Community Manager | M6 | 2000 | 2500 | — | Events, partnerships
CTO | M18 | 6500 | 8125 | 1-3% ESOP | Engineering leadership
Engineer 1 | M20 | 4500 | 5625 | ESOP | Under CTO
Engineer 2 | M23 | 4500 | 5625 | ESOP | Under CTO
Monthly Payroll Totals (Employer Cost incl. taxes)
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
Timu (CEO) | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208
Daria (COO) | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208
Space Staff (Midijob) |  |  |  | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538 | 1538
Community Manager | [5 empty] | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
CTO | M18: 8125; M19: 8125; M20: 8125; M21: 8125; M22: 8125; M23: 8125; M24: 8125
Engineer 1 | M20: 5625; M21: 5625; M22: 5625; M23: 5625; M24: 5625
Engineer 2 | M23: 5625; M24: 5625
TOTAL MONTHLY PAYROLL | 10416 | 10416 | 10416 | 11954 | 11954 | 14454 | 14454 | 14454 | 14454 | 14454 | 14454 | 14454 | 14454 | 14454 | 14454 | 14454 | 14454 | 22579 | 22579 | 28204 | 28204 | 28204 | 33829 | 33829